## V.1 Changes
LAWS Microsite — V.1 Review Changes
Feedback dated 21 Aug 2026. Implemented 10 Sep 2026. Live at https://qar1us.github.io/LAWS-microsite/
Request | Implementation | Status | Notes
§ Landing page
Change headline to “The Machines Are Already Choosing Targets” | Headline updated; set over two lines, title case, no full stop. | Done
Replace description paragraph with “Dozens of lethal autonomous weapon systems…” | Reviewer copy used verbatim. The live system/country counts it replaced are gone from the sentence. | Done | Marked “request input from NSSC team” — treat as provisional.
Keep the numbers chart; decide which numbers to keep | All four kept: systems fielded, confirmed combat use, no per-engagement approval, operator countries. | Your call | Headline now says “Dozens” while the bar shows 83 just below. Tell me which to drop.
§ Section 01 — The Spectrum of Human Control
Keep headline | No change. | Done
Use revised description copy | Reviewer copy used verbatim. | Done
Progress bar at the bottom of each class box is confusing | Removed. The count alone now carries the comparison. | Done | It was share-of-dataset, not progress. Colour coding kept as requested.
Make the B1 disclaimer a hover pop-up on the B1 icon | Info icon beside “B1”; popup on hover and on keyboard focus. | Done | Focus support added so it is reachable without a mouse.
“Link loss” is unclear — change to “signal or communication loss” | Reworded in the B1 class description and in the popup. | Done
§ Section 02 — The Tracker
Change header to “The Systems.” | Header and section kicker updated. | Done | Marked “request input from NSSC team”.
Remove IND-LAND-001, IRN-LAND-001, IRN-AIR-001 | Removed at the data build, so all counts, filters and charts follow automatically. | Done | 86 → 83 systems; 68 → 65 with combat use; 17 → 15 origin countries.
§ Section 03 — The Landscape
Move to a separate sub-page | New landscape.html, linked from the nav and from a call-out on the tracker. | Done
Need more colours for the bar graphs | Categorical palette for domain, single-hue ramps for ranked origin and operator, existing colours for autonomy class. | Done | Palette run through the chart colour validator (contrast and colour-blind separation) rather than picked by eye.
List the manufacturer/developer companies for each country | Added: 15 producing countries, roughly 105 firms, ordered by systems contributed. | Done | Firm names shown exactly as recorded. Source spells some inconsistently — see data queries below.
Map to visualise concentration by origin country | Not built. | Deferred | Listed under “Potential additions”. Needs a geographic dataset or a mapping library — a real change to the current no-dependency build. Say the word and I will scope it.
§ Section 04 — Methodology & Limits
Remove all, pending Rachel's further thoughts | Section removed from the page. | Done | Rendering code left wired so it returns without a rebuild. Note this also removed the excluded-systems annex, which the methodology says exists so omissions are visible rather than silent.
§ Miscellaneous
Add conflict use / deployment evidence where applicable | Promoted out of the record table into its own callout with theatre and targets engaged. | Done | Your open question — all cases or one example? Currently every case the analyst recorded; many entries already list several.
Add a description of each system (what it is, what it does) | Not implemented. | Blocked | The workbook has no description field, and Analyst Notes are commentary rather than description. Needs a new column in the Systems sheet — I will not write capability descriptions from my own knowledge and present them as dataset content.
Remove “Mission Planning” from autonomy by function | Dropped at the data build; matrix now 18 functions. | Done
Check copyright rules surrounding photos | Audited. 103 of 155 images are third-party editorial (BBC, NYT, Forbes, Janes and similar); 52 are government, Wikimedia or manufacturer. | Your call | All 155 are publicly downloadable and have been since 19 Aug. Restricting the page to the 52 cleared images is a one-line change.
Request input from Communications (Gio or Chris) on delivery mechanism | Not started — outside the build. | Not started | Flagged in the feedback as a prerequisite. Owner: you.
§ Found while implementing (not requested)
Bar graph fills were invisible | Fixed. The fill element was an inline span, so its height was never applied. | Done | Every bar fill had been zero-height since the tracker was built — the bars in V.1 were empty outlines.
Card titles overlapped the confidence label | Fixed by nesting the title inside the image, its intended positioning context. | Done | Fixed 10 Sep, before this feedback pass.
NOR-AIR-001 carries photos of a different system | Not changed — flagged only. | Blocked | The ID was reassigned between dataset versions: it now means Joint Strike Missile but its two photos were collected when it meant Naval Strike Missile. A workbook decision for ML.